## Sheet1
Question | Task | Sub Task | Deadline | Owner | Status | Comments
1. Use this data and/or any other data you find to select 2 cities to pitch to the NBA as prime locations for the association’s expanse | What are the two cities that your team sees as the best options to place a new team in? How did your team come to this conclusion? | 1. Review and understand Datathon databases |  | Thilak Cebolu Mohan | Completed
|  | 2. Literature Review to find factors related to location choice | 2024-02-03 | Tania Camila Lamprea Barragan | Completed | All finding are posted in this document https://docs.google.com/spreadsheets/d/1yPKHJ1_hq-k_aXIkV_30IL2n2b2_utyY/edit?usp=drive_link&ouid=108248730340411207931&rtpof=true&sd=true
|  | 3. Supplement the current with required additional data | 2024-04-03 | Tania Camila Lamprea Barragan | Completed
|  | 4. Make Tableau visualization |  | Sivani Dronamraju Swathi Baskaran | In Progress
|  | 5. Mapping the data |  | swathi | In Progress
|  | 6. Write main messages or findings | 2024-04-04 | Tania Camila Lamprea Barragan | Completed
2. The NBA would like to understand estimated revenue and costs associated with this new location. | How much capital will the NBA need to spend to cover the costs associated with the new location? | 1. Review the data and select possible cost variables |  | Tania Camila Lamprea Barragan | Completed
|  | 2. Literature Review in how to estimate in the sport industry |  | Tania Camila Lamprea Barragan | Pending
3. Do the calculation of the total costs based on the data provided
| Estimate the annual revenue generated for the new team's major revenue streams. How long will it take to break even? | 1. Review the data and select possible cost variables |  | Sweta Dantu Sivani Dronamraju | In Progress | https://www.untaylored.com/post/the-business-model-and-revenue-streams-of-nba-explained
2. Literature Review in how to estimate in the sport industry
|  | 3. Do the calculation of the total costs based on the data provided |  | Thilak Cebolu Mohan
| Perform an analysis on the best sponsor for this new NBA team considering factors such as brand alignment, social media engagement, and potential financial impact. | 1. Review current sponsor of NBA and related sport in US |  | Tania Camila Lamprea Barragan | Completed
|  | 2. Review the regulation related to sport sponsors |  | Tania Camila Lamprea Barragan | Completed
3. Find the more representatives companies within the two selectec cities.
|  | 4. What are the values of the companies found/ optional brand equity scores |  | William Alejandro Moreno Mendez | Completed
|  | 5. Among the two selected cities, calculate the power market based on market share |  | William Alejandro Moreno Mendez | In Progress
6. Write the main messagea about finding of this first part
|  | 7. Review from the provided or supplemental one, how to calculate social media engagemene |  | William Alejandro Moreno Mendez | In Progress
|  | 8. Review how to calculate the potential financial impact of the sponsorship |  | William Alejandro Moreno Mendez | In Progress
3. The NBA would like to preemptively create a promotional plan for the new team you selected above | Based on your analysis and/or research of the new city and fanbase, propose a team mascot and team colors. Why that mascot? Why those colors? | 1. Take the previous information about local businesses to understand the culture to provide a mascot. | 2024-04-07 | William Alejandro Moreno Mendez | Completed | Salmon: Several species of salmon, including Chinook, coho, and sockeye, are native to the waters of the Pacific Northwest, including the rivers and streams around Seattle. Salmon plays a crucial role in the region's ecosystem and cultural heritage.
|  | 2. Review colors theory to select the most appropiate ones to convey the message of the team and sponsors | 2024-04-07 | William Alejandro Moreno Mendez | Completed | Colors: Green because all Seattle teams use it and we want to reinforce that bond. Also, the previous tema also used the green color. Also, this color represents the sustainability and enviromental mindset of the region. Then the earth tones is to reflect the grund connection that comes from the indigenous, european settlers. Also the earth tone set us apart of the previous team and the other NFL and MLS teams in the region. But also, set us appart of the Boston Celtics that also use green as their main color
| How might the NBA promote this team to the new city to maximize brand awareness and fanbase growth? | 1. Create an STP plan (Segmentation, Target and promotion) | 2024-04-07 | William Alejandro Moreno Mendez | Completed
|  | 2. Using the 4Ps frame to create the marketing strategy | 2024-04-07 | William Alejandro Moreno Mendez | Completed
| Despite the NBA not being an inherently global brand, one executive wants to explore the possibility of growing a fanbase for the new team in an international market. Select a country you recommend they target and explain why this market could be a successful endeavor for the NBA. | 1. Search for continent data to know where Basketball is popular |  | Sweta Dantu | In Progress | https://today.yougov.com/sport/articles/35690-nba-following-outside-its-home-market , Have to search data similar to this to get a better evalutaion https://pr.nba.com/nba-philippines-2022-23-season/#:~:text=618%20million%20%E2%80%93%20The%20Philippines%20accounted,country%20outside%20of%20the%20U.S. https://sports.inquirer.net/436977/filipinos-remain-one-of-top-nba-viewers-for-2020-2021-season
2. Make the same analysis done in the first part but at world level country
3. write the main findings
| What technology would you use to support the marketing, logistical, and/or management efforts for the new team? Case Questions | Share the platform we are going to use for the marketing promotion | 2024-04-07 | William Alejandro Moreno Mendez | Completed